WORK PLAN FOR THE AQUATIC ANIMALS COMMISSION

Items proposed for adoption at the May GS 2022

| Aquatic Code |  |  |  |
| --- | --- | --- | --- |
| Chapter/Subject | Status |  |  |
|  | September 2021 | February 2022 | May GS 2022 |
| User’s Guide | Reviewed amended articles and presented for comments | Review comments (1st round) | Propose for adoption |
| Glossary definitions: ‘Competent Authority’, ‘Veterinary Authority’ and ‘Aquatic Animal Health Services’ | Reviewed comments (1st round) and presented for comments | Review comments (2nd round) | Propose for adoption |
| Glossary definitions: ‘Basic biosecurity conditions’, ‘Biosecurity plan’, ‘Early detection system’ and ‘Passive surveillance’ | Reviewed comments (1st round) and presented for comments | Review comments (2nd round) | Propose for adoption |
| Chapter 1.3. Listing of infection with tilapia lake virus (TiLV) | Reassessed infection with TiLV for listing | Review comments (1st round) | Propose for adoption |
| Chapter 1.4. Aquatic Animal Health Surveillance | Reviewed comments (1st round) | Review comments (2nd round) | Propose for adoption |
| Model Articles X.X.4. to X.X.8. for disease-specific chapters to address declaration of freedom from [Pathogen X] | Reviewed comments (2nd round) | Review comments (3rd round) | Propose for adoption |
| Safe commodities – Crustacean diseases – Articles 9.X.3. | Reviewed comments (1st round) | Review comments (2nd round) | Propose for adoption |
| New Chapter 9.X. Infection with decapod iridescent virus 1 | Reviewed draft chapter and presented for comments | Review Comments (1st round) | Propose for adoption |
| Safe commodities – Fish diseases – Articles 10.X.3. | Reviewed amended articles and presented for comments | Review comments (1st round) | Propose for adoption |
| Chapter 10.1. Infection with epizootic haematopoietic necrosis virus | Reviewed amended articles and presented for Member comments | Review 1st round Member comments | Propose for adoption |
| Chapter 10.7. Infection with koi herpes virus | Reviewed amended articles and presented for Member comments | Review 1st round Member comments | Propose for adoption |
| Susceptible Species – Infection with abalone herpesvirus – Articles 11.1.1. and 11.1.2. | Reviewed ad hoc Group report and presented the revised articles for comments | Review Comments (1st round) | Propose for adoption |
| Susceptible Species – Infection with Bonamia exitiosa –Articles 11.2.1. and 11.2.2. | Review comments (1st round) | Review comments (2nd round) | Propose for adoption |
| Aquatic Manual |  |  |  |
| Chapter/Subject | Status |  |  |
|  | September 2021 | February 2022 | May GS 2022 |
| Chapter 2.3.0. General information (diseases of fish) | Update Section 2.5 and presented for comments | Review comments | Propose for adoption |
| Chapter 2.3.4. Infection with HPR-deleted or HPR0 infectious salmon anaemia virus | Reviewed Member comments (1st round) and presented for comment | Review comments (2nd round) | Propose for adoption |
| Chapter 2.3.6. Infection with koi herpesvirus | Reviewed comments (1st round) and presented for comment | Review comments (2nd round) | Propose for adoption |
| Sections 2.2.1., 2.2.2. of Chapter 2.4.1. Infection with abalone herpesvirus | Reviewed ad hoc Group report and presented revised articles for comments | Review comments (1st round) | Propose for adoption |
| Sections 2.2.1., 2.2.2. of Chapter 2.4.2. Infection with Bonamia exitiosa | Reviewed comments (1st round) and presented for comments | Review comment (2nd round) | Propose for adoption |

On-going work for adoption in 2023 or later

| Aquatic Code |  |  |  |
| --- | --- | --- | --- |
| Chapter/Subject | Status |  |  |
|  | September 2021 | February 2022 | September 2022 |
| Monitor emerging diseases and consider any required actions | On-going |  |  |
| Chapter 4.X. New draft chapter on Emergency disease preparedness | Requested an ad hoc Group be convened | Consider ad hoc Group report | AAC Review of proposed Chapter 4.X. |
| Chapter 4.Y. New draft chapter on Disease outbreak management | ad hoc Group to be convened | ad hoc Group to start drafting after completion of Chapter 4.X. | ad hoc Group to start drafting after completion of Chapter 4.X. |
| Safe commodities – Amphibians –Articles 8.X.3. |  | Review amended articles and present for comments | Review Comments (1st round) |
| Article 9.3.1. of Chapter 9.3. Infection with Hepatobacter penaei (Necrotising hepatopancreatitis) |  | Review amended articles and present for comments | Review Comments (1st round) |
| Susceptible Species – Articles 9.4.1. and 9.4.2., Infection with infectious hypodermal and haematopoietic necrosis virus (IHHNV) |  | Review amended articles and present for comments | Review Comments (1st round) |
| Susceptible Species – Fish diseases – Articles 10.X.1. and 10.X.2. for: - Infection with Red seabream iridovirus/infectious - Infection with Aphanomyces invadans (Epizootic ulcerative syndrome |  | Ad hoc Group reconvened: Assessment for RSIV/ISKNV planned for April 2022 | Review ad hoc Group report |
| Susceptible Species Assessment of new species for previously assessed diseases as necessary | As needed |  |  |
| Chapter 10.X. Infection with tilapia lake virus (pending adoption) |  |  | Review draft chapter and present for comment |
| Susceptible species – Fish diseases – Articles 11.X.1. and 11.X.2. for: - Infection with Marteilia refringens - Infection with Xenohaliotis californiensis - Infection with Perkinsus marinus - Infection with Perkinsus olseni | Requested ad hoc Group continue its assessments | Next ad hoc Group meeting planned for June 2022 | Review ad hoc Group report |
| Safe commodities – Mollusc diseases – Articles 11.X.3. |  | Review amended articles and present for comments | Review Comments (1st round) |
| Aquatic Manual |  |  |  |
| Chapter/Subject | Status |  |  |
|  | September 2021 | February 2022 | September 2022 |
| The use of environmental DNA methods for aquatic animal disease surveillance | Reviewed comments (1st round) | Review Member comments, revise and upload onto OIE website |  |
| Levels of validation and the test scoring system in Table 4.1 | Reviewed comments and sent to Reference Laboratories for feedback | Review feedback from Reference Laboratories |  |
| Section 2.2. General provisions – Crustaceans |  |  | Review amended Chapter and present for comments |
| Chapter 2.2.1. Acute hepatopancreatic necrosis disease |  | Updated and reformatted and presented for comments | Review comments (1st round) |
| Chapter 2.2.2. Infection with Aphanomyces astaci (Crayfish plague) |  | Updated and reformatted | Review further updated draft and present for comments |
| Chapter 2.2.3. Infection with Hepatobacter penaei (necrotising hepatopancreatitis) |  | Updated and reformatted and presented for comments | Review comments (1st round) |
| Chapter 2.2.4. Infection with infectious hypodermal and haematopoietic necrosis virus |  | Updated and reformatted and presented for comments | Review comments (1st round) |
| Chapter 2.2.6. Infection with Macrobrachium rosenbergii nodavirus (white tail disease) |  | Updated and reformatted | Review further updated draft and present for comments |
| Chapter 2.2.X. Infection with decapod iridescent virus 1 |  |  | Develop draft chapter for review |
| Chapter 2.3.2. Infection with epizootic haematopoietic necrosis virus | Updated and reformatted and presented for comments | Review comments (1st round) | Review comments (2nd round) |
| Chapter 2.3.1. Infection with Aphanomyces invadans (epizootic ulcerative syndrome) | Updated and reformatted | Review further updated draft and present for comments | Review comments (1st round) |
| Chapter 2.3.7. Red sea bream iridoviral disease | Updated and reformatted and presented for comments | Review comments (1st round) | Review comments (2nd round) |
| Chapter 2.3.X. Infection with tilapia lake virus (Pending adoption) |  |  | Develop draft chapter for review |

Newly prioritised items to commence before May 2024

| Aquatic Code |  |  |  |
| --- | --- | --- | --- |
| Chapter/Subject | Status | First Priority | Second Priority |
| Safe Commodity Assessments (for all listed diseases) | Review of any new scientific evidence to update standards if necessary | ✓ |  |
| Chapter 1.3. Diseases listed by the OIE | Review any new diseases for listing or de-listing as necessary | On going |  |
| Chapter 4.2. Zoning and Compartmentalisation | Re-develop chapter to focus solely on zoning |  | ✓ |
| Chapter 4.3. Application of Compartmentalisation | Re-develop chapter to improve guidance and align with new Chapter 4.1 on biosecurity. | ✓ |  |
| Section 5. New Chapter on ornamental aquatic animals | Development of new standards to facilitate safe trade of ornamental aquatic animals | ✓ |  |
| Section 5. New Chapter on genetic materials | Development of new standards to facilitate safe trade of genetic materials | ✓ |  |
| Articles 9.X.1. and 9.X.2. Update lists of susceptible species | Remaining crustacean diseases for review: - Infection with Aphanomyces astaci (Crayfish plague) - Infection with white spot syndrome virus |  | Dependant on the completion of work to update the assessments of species susceptible to all fish and mollusc OIE listed diseases |
| Aquatic Manual |  |  |  |
| Chapter/Subject | Status | First Priority | Second Priority |
| Chapters 2.2.X. Crustacean disease specific chapters | Update and reformat chapters using the new template (Infection with IMNV, TSV, WSSV, YHV) | ✓ |  |
| Section 2.4. General provisions – Molluscs | Review and update the introductory chapter on mollusc diseases |  | ✓ |
| Chapters 2.4.X. Mollusc disease specific chapters | Update and reformat chapters using the new template (all diseases) |  | ✓ |